OneVA Pharmacy Implementation

**Meeting Information**

|  |  |  |  |
| --- | --- | --- | --- |
| **Discussion:** | OneVA Pharmacy Implementation Daily Scrum Meeting | | |
| **Date of Meeting:** | 02/18/2015 | **Location:** | Teleconference |
| **Facilitator:** | Cecelia Wray | | |
| **Time:** | 2:30 pm-3:00 pm | | |

|  |  |  |  |
| --- | --- | --- | --- |
| Attendee Name (P=Present) | | | |
| Birali Hakizumwami |  | Brad Fisher | **P** |
| Cecelia Wray | **P** | Tony Burleson | **P** |
| Kathy Coupland | **P** | Sherri Simons |  |
| Bill Walsh | **P** | TJ Cope | **P** |

**Action Items Outstanding**

| Priority | Open / Closed | Origin  Date | Action Item | Owner | Due Date | Date Completed |
| --- | --- | --- | --- | --- | --- | --- |
| H | O | 12/09/15 | VA Access: TJ Process the Elevated Privileges (EP) Forms | TJ resubmitted access | 02/19/16 |  |
| H | O | 02/10/16 | Team awaiting updated project schedule with milestone dates | Cecelia/Mike Fauber | 02/19/16 |  |
| H | O | 12/22/15 | Team awaiting VAeMI Development & Testing Environment | Mike Fauber | 02/19/16 |  |
| H | O | 02/16/16 | Team awaiting VAeMI EDE Development Environment | Russ | 02/29/16 |  |
| H | O | 02/10/16 | Team waiting access to VAeMI Testing Environment | Ruth | 02/29/16 |  |
| H | O | 02/16/16 | Birali VA Network Access | Kit | 02/29/16 |  |
| H | O | 01/11/16 | Team waiting on GFEs | Josh | 02/19/16 |  |
| H | O | 02/05/16 | eToken for Tony, Kathy, TJ | Kathy resubmitted; Tony waiting | 02/29/16 |  |
| M | O | 02/12/16 | Team enter tasks on Rational Tool | Brad/Kathy/ TJ/Tony | 02/29/16 |  |
| L | O | 12/09/15 | Smoke testing and ensure eMI box is set up and HDR/CDS access is available & MVI is working. | TJ Cope / Tony Burleson / Brad | TBD |  |
| L | O | 12/09/15 | Documentation: Send OneVA Pharmacy components to Initial Operating Capability (IOC) sites for testing | Brad Fisher / Tony Burleson | TBD |  |
| L | O | 12/09/15 | Testing: Validate software meets requirements via Skype | Rob Silverman work with TJ | TBD |  |
| L | O | 12/09/15 | Documentation: Develop Sustainment Transition Plan (Health Product Support possibility) | Cecelia / Bill / Joshua discuss Kathy to author | TBD |  |
| L | O | 12/30/15 | Open Ports for Capture Agents to be Installed on testing environment | Brad/Tony | TBD |  |
| L | O | 12/30/15 | SEDR: Define the data to be captured | Brad/Tony | TBD |  |
| L | O | 12/30/15 | SEDR: Run Tests to Capture Data | Brad | TBD |  |
| L | O | 12/30/15 | SEDR: Install Capture Agents on Servers and Client | Brad/Tony | TBD |  |
| L | O | 01/04/16 | Documentation: Patch Description and Install Guides (2) to Kayleen Zimmerman | Brad/Kathy | 03/24/16 |  |
| L | O | 01/21/16 | Apply patch 427 and 444 | Brad | 04/06/16 |  |

| **Discussion Notes** |
| --- |
| * Bill asked Tony to explain the BAR file, monitoring, auditing, and configuration of the VAeMI. Tony provided the explanation that we will give a deployable BAR file to the VAeMI team and it does not include monitoring, auditing, logging, network connectivity, or QA for example; those are outside the BAR file. He explained the BAR file contained the message flow for the OneVA Pharmacy application. Kathy asked about installation guide and if there would be a BAR file and steps for configuration. Tony said yes and he would walk through the process and steps with Kathy. Tony thought it was a good idea to get started on the guide sooner than later because he believes he is 90% complete. His remark “Let’s do it now”. Kathy will schedule working session with Tony for next week. * Cecelia explained that in the HDR/CDS development environment, they are not able to connect with MVI and therefore they will enter the ICN numbers manually in IAM (Identify Access management.) * Bill asked if the MVI call in the MUMPS code was going to be removed and TJ clarified that it was agreed it was not needed. * TJ asked Cecelia to walk through her diagram and explain the MVI issue to be clear on what isn’t going to be available in development. * Cecelia reported the IPT was uneventful as there were no updates from the VAeMI with the exception that the contract modification was still underway and that it would be most likely 2-weeks before they provided her with a project schedule. * Cecelia told Tony that she gave his name as Point of Contact and that if he didn’t hear back from Ruth about the software and license by end of day Friday, to follow up again. Tony had not signed on to his VA email account therefore he had not read the Emails from Birali or Cecelia regarding the VAeMI process. * Bill is off tomorrow. * TJ is off tomorrow and all next week but will sign on each night to read Emails and will address anything of urgent nature. * Brad spent time looking at the data dictionaries and the integration of patches 444 and 427. He sees no issues. He created the build and di the merge and used the baseline standards and conventions. He is modifying the stack and HL7 treating facility code – to remove. * Tony reported that he and Kathy met and are in sync regarding the sequence diagrams and update to the SDD * Kathy asked TJ to talk more about the exceptions he is looking to see in the SDD and sequence diagrams as Tony wasn’t planning on creating a data flow diagram. TJ spend time talking about the exceptions and Tony thought those belong in the Use Case exception flow. Tony said he coded based on the Use Case in the SDD. Kathy reported that she pulled those use cases from the prototypes. Brad indicated that the exceptions most likely are the same as he hasn’t changed any code – however, the Pharmacy Manager exception would no longer be needed. Brad suggested looking at the screens. Kathy stated she would look through the PowerPoint slides that were created in the prototype and see what she can determine regarding exceptions. TJ stated they just may have to be flushed out during testing but made a point that if we get our development site up and we are delaying the project because of issues we could tackle now; this would not look good for our team. Cecelia stated she couldn’t think of any other way so that moving forward with the suggestions discussed would make sense.   + ACTION ITEM: Kathy to review porotype and document all exceptions and create for TJ when he returns. * TJ stated he turned over the Master Test Plan to Kathy. Kathy agreed to work on it Friday. TJ isn’t comfortable enough about Rational Functional Tester since he hasn’t access the tool, to be able to update the document with detailed information, specifically on the reporting aspect but once Kathy updates it, it would be fine to be released, as long as the issues are qualified. * Cecelia asked TJ if the Word documents for test cases and scripts were able to be submitted. He shared there is much work to be done on them, as the details for prompts, exceptions, and labels are available but it could be submitted if someone isn’t looking for those issues and if you qualify that they are outstanding. * Brad reviewed the code and said there are two areas where he found check error node – with two potential messages – ESB connection issue and VistA connection issues. He suggested to review the screen shots to find the language the user would expect to see on the screen. * Bill stated that he was in communication with Ruth via IM and she stated she is getting Sergio and Vu together for quick communication and will keep him posted. |
|  |