OneVA Pharmacy Implementation

**The image displays the VA logo.

Meeting Information**

| **Discussion:** | OneVA Pharmacy Implementation Weekly IPT & Stakeholder Meeting | | |
| --- | --- | --- | --- |
| **Date of Meeting:** | 01/28/2016 | **Location:** | Teleconference |
| **Facilitator:** | Cecelia Wray | | |
| **Time:** | 12:30 – 1:00 pm EST | | |

Agenda for today:

* Project Update – see attached (Cecelia)
* Unit Functional Testing (UFT) participant’s recommendations (Rob)

| Attendee Name (P=Present) | | | |
| --- | --- | --- | --- |
| Behuniak, Loren |  | Beltran-West, Ruth | **P** |
| Bloch, Jaculyn | **P** | Bulson, Mark | **P** |
| Cortright, Michael |  | Chu, Ann | **P** |
| Cross, Heidi |  | Coupland, Kathy | **P** |
| Farber, Michael | **P** | Crespo, Pamela | **P** |
| Holt, Russ | **P** | Fisher, Brad |  |
| Johnson, Dale | **P** | Fox, Kirk |  |
| Lilly, Tomi |  | Littlefield, Patrick | **P** |
| Meneguzzo, Kim | **P** | Lyttle, Kim | **P** |
| Meyer, Nancy | **P** | McGloine, Thomas |  |
| Mingo, Fred |  | Mian, Naeem | **P** |
| Patterson, Joshua |  | Parris, Chris | **p** |
| Reese, Yolanda | **P** | Poteet, David |  |
| Sanders, Lynn |  | Roseland, Patricia |  |
| Seburn, Cindy | **P** | Santos, Roberto |  |
| Sigley, Roger |  | Smith, Gloria | **P** |
| Silverman, Robert | **P** | Spencer, Steve | **P** |
| Teague, Kit | **P** | Susarla, Narasa |  |
| Teague, Lyn | **P** | VanCamp, Philip | **P** |
| Woods, Baron | **P** | Walsh, Bill | **P** |
| Wray, Cecelia | **P** | Waltman, Dave |  |
| Miestchovich, Gaylyn | **P** |  |  |

**The image displays the VA logo.
Action Items Outstanding**

| Action Item Origination Date | Action Item | Owner | Status | Reported Closed Date |
| --- | --- | --- | --- | --- |
| 11/05/2015 | Review: [DVBA HRC MENU PHARMACY [ [PSO HRC PROFILE/REFILL] for possible use of the OneVA Pharmacy module. | Brad | Open |  |
| 12/10/2015 | Provide recommendation for IOC test patients | Rob / Cecelia | Closed | 01/21/2016 |
| 01/07/16 | IOC site have VA-eMI Middleware components to perform testing else Elevated Privileges needed for AITC access. | Cecelia | Austin will provide a script to avoid individuals requiring EP | 01/21/2016 |
| 01/21/2016 | GFEs needed for OneVA Pharmacy team members. | Joshua | Open |  |

| **Discussion Notes** |
| --- |
| * Status: Cecelia walked the audience through the OneVA Pharmacy Executive Dashboard (refer to the Dashboard and General comments below).   + OneVA Pharmacy Status:     - Overall status: Yellow     - Project Management: Red – project slipped one more week   + 4-VistA instances are set up but having challenges getting the last development patches from Forum down to the development and integration services.   + HDR/CDS: Integration underway; working through interconnections.   + MVI: Requested to move into their test environment. Uncertain at this time at the feasibility of the request.   + IOC: ICO Memo of Understanding (MOUs) created and being delivered to all 3-IOC sites.   + VAeMI: No resolution yet; discussions have started related to mitigation plans. Possibilities are the use of point-to-point / VistA Link or VIE. * User Functional Testing (UFT) will be performed on the Austin servers. There was a concern about ICO site members having to obtain Elevated Privilege (EP) but Tom Keogh created a script that will allow users to sign into the Austin integrated environment without EPs. Rob agreed to take lead/ownership of UFT. He will be involved and engage PBM team members and IOC POCs. IOC sites would not have access from their test environments to the necessary integration software this test would require, in addition to the remote VistA sites. UFT members will instead test using the OneVA Pharmacy Austin integration environments. * IOC evaluation will use production VAeMI. Evaluation to use window refills or employees who are Veterans and need to refill scripts. Cecelia to send communication shortly to IOC POCs to begin weekly meetings. * EMI: A meeting will be held at 4:30 today to discuss VAeMI for OneVA Pharmacy. Russ suggested a OneVA Pharmacy team member should attend. * Patrick Littlefield requested an update on the schedule. Cecelia reported that if VAeMI provides a testing environment next week or the mitigation option is decided and available next week, then the ePIP hand off at the end of May is still doable. To know if June is realistic for National rollout will depend upon today’s VAeMI meeting. Cecelia to get back to Patrick after the meeting. |
|  |



