OneVA Pharmacy Implementation

**The image displays the VA logo.

Meeting Information**

| **Discussion:** | OneVA Pharmacy Implementation Weekly IPT & Stakeholder Meeting | | |
| --- | --- | --- | --- |
| **Date of Meeting:** | 02/04/2016 | **Location:** | Teleconference |
| **Facilitator:** | Cecelia Wray | | |
| **Time:** | 12:30 – 1:00 pm EST | | |

Agenda for today:

* Project Update – see attached (Cecelia)

| Attendee Name (P=Present) | | | |
| --- | --- | --- | --- |
| Behuniak, Loren |  | Beltran-West, Ruth |  |
| Bloch, Jaculyn |  | Bulson, Mark | **P** |
| Cortright, Michael |  | Chu, Ann | **P** |
| Cross, Heidi |  | Coupland, Kathy | **P** |
| Farber, Michael | **P** | Crespo, Pamela |  |
| Holt, Russ | **P** | Fisher, Brad | **P** |
| Johnson, Dale |  | Fox, Kirk |  |
| Lilly, Tomi | **P** | Littlefield, Patrick |  |
| Meneguzzo, Kim | **P** | Lyttle, Kim |  |
| Meyer, Nancy |  | McGloine, Thomas |  |
| Mingo, Fred | **P** | Mian, Naeem |  |
| Patterson, Joshua |  | Parris, Chris | **P** |
| Reese, Yolanda | **P** | Poteet, David |  |
| Sanders, Lynn | **P** | Roseland, Patricia |  |
| Seburn, Cindy | **P** | Santos, Roberto | **P** |
| Sigley, Roger |  | Smith, Gloria | **P** |
| Silverman, Robert | **P** | Spencer, Steve |  |
| Teague, Kit |  | Susarla, Narasa |  |
| Teague, Lyn | **P** | VanCamp, Philip | **P** |
| Woods, Baron | **P** | Walsh, Bill | **P** |
| Wray, Cecelia | **P** | Waltman, Dave | **P** |
| Miestchovich, Gaylyn |  | Graves, Nicole | **P** |
| Simons, Sherri | **P** |  |  |

**The image displays the VA logo.
Action Items Outstanding**

| Action Item Origination Date | Action Item | Owner | Status | Reported Closed Date |
| --- | --- | --- | --- | --- |
| 11/05/2015 | Review: [DVBA HRC MENU PHARMACY [ [PSO HRC PROFILE/REFILL] for possible use of the OneVA Pharmacy module. | Brad | Open |  |
| 01/21/2016 | GFEs needed for OneVA Pharmacy team members. | Joshua | Open |  |

| **Discussion Notes** |
| --- |
| * Status: Cecelia walked the audience through the OneVA Pharmacy Executive Dashboard (refer to the Dashboard and General comments below).   + ICO Site review is moved out to 8-weeks. (Project Schedule below)   + VAeMI – No update on timeline available for VAeMI readiness. OneVA Pharmacy working on a mitigation plan. At a high-level, the team has found two Enterprise Service Bus (ESB) options that are approved on the VA TRM until end of year 2017. The plan is to submit the mitigation analysis options to VA leadership by next week. Options are to parallel the efforts of a temporary ESB for OneVA Pharmacy then cut over to VAeMI when ready; or wait until VAeMI is ready.   + Project activities will come to a standstill within the next week to ten days if VAeMI is not ready for the development team to migrate into. * Mike Farber shared that he can have an integration team start working on OneVA Pharmacy in the March/April time frame or sooner. In order to do so, however, a contract option needs to be exercised and that process in going to be started soon (the contract has not been awarded.) The production environment will be ready by September. * The discussion included the sharing that there are active briefings being made to the Under Secretary on the OneVA Pharmacy program therefore it is a highly visible project with an immediate urgency status. Someone asked about the original implementation date for OneVA Pharmacy. It was shared that the original target date for OneVA Pharmacy readiness for National Release was March 31, 2016. * Some attendees provided a concern that standing up a temporary ESB for OneVA Pharmacy may not be the wise choice, but consider instead to put resources towards getting the Enterprise VAeMI solution up and ready. It was stated that OneVA Pharmacy should be the priority implementation for the VAeMI program. Mr. Patterson asked if anyone on the call could make this decision about using a mitigation plan vs. waiting on VAeMI efforts. It was agreed that in order to give proper understanding of the options a meeting should be scheduled for next week with the VA leadership to review the mitigation analysis presentation and the VAeMI and OneVA Pharmacy project schedules, to provide the appropriate direction for the OneVA Pharmacy project. * Question was raised regarding IOC site availability for the OneVA Pharmacy evaluation since the project schedule has moved. Rob Silverman agreed to reach out to the IOC sites point-of-contacts and determine if there are any issues with the new schedule. He will report back directly to Cecelia his findings. |
|  |





