OneVA Pharmacy Middleware Mitigation Option Discuss

**The image displays the VA logo.

Meeting Information**

| **Discussion:** | OneVA Pharmacy Middleware Mitigation Option Discussion | | |
| --- | --- | --- | --- |
| **Date of Meeting:** | 02/10/2016 | **Location:** | Teleconference |
| **Facilitator:** | Birali Hakizumwami | | |
| **Time:** | 11:00 – 12:00 pm EST | | |

| Attendee Name (P=Present) | | | |
| --- | --- | --- | --- |
| Behuniak, Loren |  | Beltran-West, Ruth | **P** |
| Bloch, Jaculyn |  | Bulson, Mark |  |
| Cortright, Michael | **P** | Chu, Ann |  |
| Cross, Heidi |  | Coupland, Kathy |  |
| Farber, Michael | **P** | Crespo, Pamela |  |
| Holt, Russ | **P** | Fisher, Brad |  |
| Johnson, Dale | **P** | Fox, Kirk | **P** |
| Lilly, Tomi | **P** | Littlefield, Patrick |  |
| Meneguzzo, Kim | **P** | Lyttle, Kim |  |
| Meyer, Nancy | **P** | McGloine, Thomas |  |
| Mingo, Fred | **P** | Mian, Naeem | **P** |
| Patterson, Joshua | **P** | Parris, Chris | **P** |
| Reese, Yolanda |  | Poteet, David |  |
| Sanders, Lynn |  | Roseland, Patricia |  |
| Seburn, Cindy | **P** | Santos, Roberto |  |
| Sigley, Roger |  | Smith, Gloria | **P** |
| Silverman, Robert | **P** | Spencer, Steve | **P** |
| Teague, Kit | **P** | Susarla, Narasa | **P** |
| Teague, Lyn | **P** | VanCamp, Philip |  |
| Woods, Baron | **P** | Walsh, Bill | **P** |
| Wray, Cecelia | **P** | Waltman, Dave |  |
| Miestchovich, Gaylyn |  | Graves, Nicole | **P** |
| Simons, Sherri | **P** |  |  |

**The image displays the VA logo.
Action Items Outstanding**

| Action Item Origination Date | Action Item | Owner | Status | Reported Closed Date |
| --- | --- | --- | --- | --- |
| 01/21/2016 | GFEs needed for OneVA Pharmacy team members. | Joshua | Open |  |
| 02/11/16 | VA SharePoint Site for OneVA Pharmacy | Cecelia | Open |  |

| **Discussion Notes** |
| --- |
| * Status: Cecelia walked the audience through the OneVA Pharmacy Executive Dashboard (refer to the Dashboard and General comments below).   + Overall Status is YELLOW   + Project Management and System Set up continue to be in red.   + HDR/CDS Testing & Development Environments: Baron Woods stated Jesse Brunn is dedicated to this effort in setting up the integration and access for the OneVA Pharmacy’s use of the HDR/CDS Stage 1A environment. Narasa is actively engaged and will assist with issues. Cecelia to continue to work with the team to gain access to the development environment. * VAeMI - Mike Farber: VAeMI is currently in the middle of a contract modification so timing to replace and swap the eCMS project with OneVA Pharmacy is perfect. The submission has been made and awaiting the contract office to approve. OneVA Pharmacy was identified as a moderate effort, which was the same effort as eCMS. This will allow the Integration Team to plan for the same type of effort. As soon as the contract is signed, the Integration Team (SRA) will become engaged full force. They are prepared as they were preparing for eCMS. Mike mentioned that he and his team are fully aware of the importance of this project and its visibility, however, he stated as much as he is hoping to short step some efforts, there are still the steps that need to be taken to stand up a complete integrated environment in development and pre-production.   + Cecelia asked if there was a schedule template available. Mike explained this is the first effort so the work being done now is becoming the template. He has people who have started putting together the task list and template and will be able to supply within the next couple of days.   + Cecelia mentioned the VAeMI team has reviewed the OneVA Pharmacy SDD.   + Mike explained once permission is given to SRA to begin, they will contact the OneVA Pharmacy POC and start a weekly call. They will work with the developer through development and pre-production. If ESSCB tickets are necessary, they may need help in expediting approvals.   + Mike will provide Cecelia the task list so Cecelia can update the OneVA Pharmacy schedule and provide to Dave Waltman.   + Mike questioned the 18 month vs. 12 months vs. 6-month delivery on the OneVA Pharmacy project schedule. Rob Silverman explained that when the Innovations OneVA Pharmacy prototype was reviewed by the Undersecretary it was decided that it should be delivered by March 30th, however, the prototype contained a one-off home grown written ESB called Pharmacy Manager. The direction then came for the OneVA Pharmacy to replace Pharmacy Manager with the VAs Enterprise Standard – VAeMI.   + Mike summed up the conversation that his goal is to create a solid outline of what is realistic within the next 5 or 6 days. * IOC site availability for the OneVA Pharmacy evaluation – Rob stated there isn’t a decision yet if Denver will or will not participate in the MOCHA 2.1 Site Evaluation. He remarked if OneVA Pharmacy remains ahead of the MOCHA effort, execution of the current plan should be fine. He however stated there is a risk because the Denver POC has an annual leave gap. If both projects are scheduled for IOC Site Evaluation at the same time, the site POC may select to drop one project. * VA ForumForUs Decommission: Rob spoke about the decommission of the VA ForumForUs site. Lilly Tomi stated it was official and the site will be shut down on April 3, 2016. Rob suggested VA Pulse. Kathy is attending the Training Option Discussions next week. Cecelia suggested a VA SharePoint. Rob said a VA SharePoint would be preferred over VA Pulse because VA Pulse requires a second sign on. Cecelia to look into a VA SharePoint site for OneVA Pharmacy. |
|  |



