OneVA Pharmacy Implementation

**The image displays the VA logo.

Meeting Information**

| **Discussion:** | OneVA Pharmacy Implementation Weekly IPT & Stakeholder Meeting | | |
| --- | --- | --- | --- |
| **Date of Meeting:** | 02/18/2016 | **Location:** | Teleconference |
| **Facilitator:** | Cecelia Wray | | |
| **Time:** | 12:30 – 1:00 pm EST | | |

Agenda for today:

* Project Status (Cecelia)
* Project SharePoint site (Cecelia)
* eMI (Mike/Ruth)
  + Schedule
  + Licenses
  + Contract
  + Accreditation standing for MLLP

| Attendee Name (P=Present) | | | |
| --- | --- | --- | --- |
| Baggett, Mona |  | Baylis, Randall | **P** |
| Beckley, Robert |  | Beltran-West, Ruth | **P** |
| Behuniak, Loren |  | Bulson, Mark | **P** |
| Bloch, Jaculyn | **P** | Carroll, Daniel |  |
| Cortright, Michael |  | Chu, Ann | **P** |
| Crespo, Pamela |  | Delano, Jay |  |
| Cross, Heidi |  | Coupland, Kathy |  |
| Ellis, Donna |  | Fauber, Michael | **P** |
| Gossett, Malachy |  | Grimm, Thomas |  |
| Holt, Russ | **P** | Fisher, Brad |  |
| Johnson, Dale | **P** | Fox, Kirk |  |
| Lilly, Tomi |  | Littlefield, Patrick |  |
| Meneguzzo, Kim | **P** | Lyttle, Kim | **P** |
| Meyer, Nancy | **P** | McGloine, Thomas | **P** |
| Miestchovich, Gaylyn | **P** | Graves, Nicole |  |
| Mingo, Fred | **P** | Mian, Naeem | **P** |
| Patterson, Joshua | **P** | Parris, Chris | **P** |
| Pearcy, Patrick |  | Pierson, Yvonne |  |
| Reese, Yolanda | **P** | Poteet, David |  |
| Sanders, Lynn |  | Roseland, Patricia | **P** |
| Seburn, Cindy |  | Santos, Roberto | **P** |
| Sigley, Roger |  | Smith, Gloria | **P** |
| Silverman, Robert | **P** | Spencer, Steve | **P** |
| Simons, Sherri |  | Linville, Kathleen |  |
| Spence, Fred |  | Temkin, Josh |  |
| Teague, Kit | **P** | Susarla, Narasa |  |
| Teague, Lyn | **P** | VanCamp, Philip |  |
| Tirrell, John |  | Zawierucha, Staci |  |
| Woods, Baron |  | Walsh, Bill | **P** |
| Wray, Cecelia | **P** | Waltman, Dave |  |

**The image displays the VA logo.
Action Items Outstanding**

| Action Item Origination Date | Action Item | Owner | Due Date /Status | Reported Closed Date |
| --- | --- | --- | --- | --- |
| 01/21/2016 | GFEs needed for OneVA Pharmacy team members. | Joshua | 02/29/16 / Open |  |
| 02/11/16 | VA SharePoint Site for OneVA Pharmacy | Cecelia | Closed | 02/18/16 |
| 02/10/16 | OneVA Pharmacy -VAeMI Integrated Master Project Schedule | Cecelia/ Mike | 02/29/16 / Open |  |
| 02/18/16 | Modify VAeMI Integration contract to exchange the eCMS for OneVA Pharmacy. | Mike Fauber | 02/19/16 / Open |  |
| 02/18/16 | Provide Testing (SQA) Integration VAeMI site to OneVA Pharmacy | Ruth | 02/29/16 / Open |  |
| 02/18/16 | Provide SRA DEV VAeMI site to OneVA Pharmacy | Ruth | 02/22/16 / Open |  |
| 02/18/16 | What is the accreditation standing for new MLLP end to end points for each new VistA instance for each MLLI. | Mike/Ruth | 02/22/16 Open |  |
| 02/18/16 | Provide eMI software and license to OneVA Pharmacy POC Tony Burleson | Ruth | 02/22/16 / Open |  |
| 02/18/16 | Provide eMI Installation guide to OneVA Pharmacy POC Tony Burleson | Ruth | 02/22/16 / Open |  |

| **Discussion Notes** |
| --- |
| * Status: Cecelia walked the audience through the OneVA Pharmacy Executive Dashboard (refer to the Dashboard and General comments below).   + Overall Status is RED   + Hand off to EPIP is August.   + 3 test environments have been identified; team has access to 2 of those environments and form 9957 has been submitted to gain access to the 3rd.   + There is an issue in the test environment with the ability to process a prescription refill successfully. The team is working through the issue.   + Working with the HDR team to ensure the 3 VistA instances are connected to the same HDR/CDS repository that will be used for testing.   + EPIP provided a server to stand up a development VAeMI environment. Working with the VAeMI team to get the software license and installation guides.   + 3 VistA IP addresses were sent to Ruth for VAeMI configuration in their test environment.     - Ruth stated she received them and is working on getting the connectivity completed.   + VA SharePoint was set up for the OneVA Pharmacy. The URL is as follows:   <http://vaww.oed.portal.va.gov/pm/iehr/vista_evolution/pharmacy/OneVAPharm/SitePages/Home.aspx>   * VAeMI: Mike Fauber shared that progress is being made on getting the VAeMI contract awarded and integrating the OneVA Pharmacy project into that contract. He estimates the contract will be completed by this Friday. He shared that once completed, the Message Flow Team (aka integration team) will be ready to start next week. Both the Integration Team and the OneVA Pharmacy team can begin meeting next week and talk about the tasks and develop the schedule. They will also involve Ruth.   + Mike reported he does not have a project schedule to provide at this time   + Ruth is working on connections   + Ruth must reach out to Vu to understand what version of the software she needs to supply to the OneVA Pharmacy team.   + Mike and Ruth had not read the Email about the MLLP accreditation yet but Mike pulled it up during the meeting. Cecelia requested they review and reply as Dr. Pearcy thought they would know the answer.   + Mike said that once the contractor is officially engaged, he believes a project schedule could be developed within 2 weeks. He shared with Joshua that his team will be fully engaged with OneVA Pharmacy as soon as the contract is awarded.   + Demetrious is a contact for some things but Mike and Ruth are the primary point of contacts right now.   + Fred Mingo asked about the 100+ VistA connections and if they are available in the environment. It was reported there are 130 production versions of VistA.     - Mike stated there is an integration effort under the VAeMI umbrella called VistA exchange. When that migration is fully engaged, connections to all VistAs will be in place. |
|  |



