## Cover
Department of Veterans Affairs
Risk and Issue Log/Registry OneVA Pharmacy
2016-02-22
Version 2.0

## Revision History
Revision History
Date | Version | Description | Author
10/29/2015 | 1 | Initial Risks | TJ Cope
02/22/2016 | 2 | Updated Risk and Issues Log | Cecelia Wray

## Risk Log
Risk Identification Log (Initial Required Fields *)
Project*: |  | OneVA Pharmacy Implementation |  |  | Program*: |  |  |  | Product: OneVA Pharmacy Implementation |  |  |  | Product/Platform Management: VistA/Java
Project Manager*: |  | Cecelia Wray |  |  | Program Manager*: | Sherri Simons |  |  |  |  | Risk Coordinator*: Cecelia Wray/Kathy Coupland
Risk ID# * | Risk Name (short title) * | Risk Priority | Date Risk Record Opened * | Date Risk was Identified * | Risk Statement/Description (If…then…) * | Risk Category * | Risk Probability * (VH,H, M, L, VL) | Root Cause * | Risk Impact * (VH,H,M,L,VL) | Risk Response * (Accept, Avoid, Exploit, Enhance, Transfer, Share, Mitigate) | Risk Response Strategy * | Risk Trigger | Current Status * | Follow-up Date | Timeframe (Milestone, Gateway, Increment) | Risk Owner * | NOTES
| Development Environment | 2 | 2015-10-27 | 2015-09-30 | If the development environment is not available by 12/1/15 then the project may not meet the timelines. |  | M | Schedule | High | Mitigate | Develop in Innovation Sandbox | Date | Closed | 2015-10-30 | Increment | Fisher/Burleson | Development environment received
| SQA Environment | 2 | 2015-10-27 | 2015-09-30 | If the SQA environment is not available by 12/1/15 then the project may not meet the timelines. |  | M | Schedule | High | Mitigate | Test in Innovation Sandbox | Date | Closed | 2015-10-30 | Increment | Cope | SQA systems are being set up
| VistA Team Availability | 3 | 2015-10-27 | 2015-09-30 | If the VistA patch team is not available by11/6/15 then the project may not meet the timelines |  | M | Schedule | High |  |  | Date | Closed | 2015-10-30 | Increment | Fisher | Brad Fisher and Cecelia Wray invited to the VistA Patch call.
| Approved RSD | 3 | 2015-10-27 | 2015-09-30 | If the RSD is not approved by 11/15/15 then the project may not meet the timelines |  | M | Schedule | High | Mitigate | Start on requirements that appear the most stable | Date | Closed | 2015-10-30 | Increment | Fisher/Burleson | RSD signed by business as approved
| VA Access | 3 | 2015-10-27 | 2015-09-30 | If the team does not have VA Access by 12/4/15 then the project may not meet the timelines |  | M | Schedule | High | Mitigate | Use the Innovation Sandbox as much as possible | Date | Closed | 2015-10-30 | Increment | Patterson | Moved to Issue
| eMI Team Availabliity | 3 | 2015-10-27 | 2015-09-30 | If the eMI team is not available by November 6, 2015 then the project may not meet the timelines |  | M | Schedule | High | Mitigate | Get access to eMI website; understand which Websphere and MQ version are being used; download free trial. | Date | Closed | 2015-10-30 | Increment | Fisher | eMI team had a call with the team on 11/4/15.
| HDR/CDR Team Availability | 3 | 2015-10-27 | 2015-09-30 | If the HDR/CDR team is not available by 11/6/15 then the project may not meet the timelines |  | M | Schedule | High |  |  | Date | Closed | 2015-10-30 | Increment | Fisher | HDS resources attending stakeholder calls
| Prototype vs. Release Version | 3 | 2015-10-28 | 2015-10-27 | If the prototype does not meet the need of the business in the way the decoupling from the main logic was done since there is not a written requirement it may impact the timelines. |  | M | Schedule | High | Mitigate | Bring this up with the stakeholders for a discussion | Stakeholder call | Closed | 2015-11-06 | Increment | Wray | Review of the RSD was done and approved by the stakeholders.
| eMI Interfacing | 1 | 2015-11-05 | 2015-11-04 | If the eMI team is not able to start interfacing with the OneVA Pharmacy product by 11/20/15 then the project may not meet the timelines. |  | H | Schedule | High | Mitigate | Discuss with architects a method to communicate between sites | eMI call | Closed | 2015-11-10 | Increment | Wray | Project interfaced with eMI team and work is progressing
|  |  |  | 2015-11-10 | If the IOC sites are not identifed by 12/4/15 then the project may nto meet the timelines |  | H | Schedule | High | Avoid | Proactively work with the business stakeholders to identfy appropriate IOC sites | IPT call | Closed | 2015-11-19 | Increment | Wray | Moved to Issue
|  |  |  | 2015-11-25 | ISSUE: There are no systems set up in the VA network to do end to end test systems |  | H | Schedule | High | ISSUE | Issue has been communicated to the VA COR for follow up. |  | Closed
|  |  |  | 2015-11-25 | ISSUE: VistA Intake Program has stated this product is to complex to be accepted in this program. |  | H | Schedule | High | ISSUE | Issue has been communicated to the VA COR for follow up. |  | Closed |  |  |  | Issue was resolved with the VIP taking the project.
|  |  |  | 2015-12-14 | ISSUE: Three team member still do not have VA Access. |  | H | Schedule | High | ISSUE | Issue has been communicated to the VA COR for follow up. The team has been working closely with Kit Teague. |  | Closed |  |  |  | The two resources in Hawaii need to get their PIV cards. This has been schedued for first week in Januaray
|  |  |  | 2015-12-29 | If the system is not set up to receive updated patches then the schedule will be further delayed |  | H | Schedule | High | Mitigate | Work closely with system support to ensure that FTP is set up. |  | Closed | 2016-01-08 | Increment | Fisher | Developer was able to access FTP patches on 1/7/16.
|  |  |  | 2015-12-07 | ISSUE: IOC Sites have not been confirmed. |  | H | Schedule | High | ISSUE | All three sites have been confirmed. |  | Closed |  |  |  | Two of the three identified IOC sites have agreed to become test sites (Denver and SLC). .
|  |  |  | 2016-01-11 | ISSUE: The patching could not be completed last week based on unavailibity of FTP and the system was not as up to date as previously stated. |  | H |  | High | ISSUE | The project will be delayed and additional week to update the patches. |  | Closed
|  |  |  | 2015-12-14 | If the servers recently provided by the VistA Intake Program (VIP) cannot connect to HDR in the appropriate time frame then the project may be further delayed |  | M | Schedule | High | Mitigate | Work closely with both the HDR resources to ensure connections can be completed. | System Setup | OBE | 2016-01-15 | Increment | Fisher/Burleson
|  |  |  | 2015-12-14 | If the servers recently provided by the VistA Intake Program (VIP) cannot connect to MVI in the appropriate time fram then the project may be further delayed |  | H | Schedule | High | Mitigate | Work closedly with the MVI group to ensure the connection can be completed. | System Setup | OBE | 2016-01-15 | Increment | Fisher/Burleson
|  |  |  | 2016-01-07 | ISSUE: The team requires elevated privleges to access the develop/test systems |  | M |  | High | ISSUE | VA COR has been facilitating the access. |  | Closed
|  |  |  | 2016-01-07 | If the eMI framework does not accommodate all 146 VistA sites then the project could be delay until issues are resolved |  | M | Schedule | High | Avoid | Do as much testing as possible to accommodate the eMI ESB. Roll out the patch in a controlled schedule. | Deployment | Open | 2016-03-07 | Increment | VIP
|  |  |  | 2015-11-16 | ISSUE: The team has not been able to integrate with the eMI team and the schedule has extended past the POP |  | H | Schedule | High | ISSUE | Issue has been communicated to the VA COR for follow up. Plan B: Utilize another ESB on TRM; Risk-cost and time delay to set up system at AITC |  |  |  |  | Patterson
|  |  |  | 2016-01-28 | ISSUE: The project has to move from the EPIP servers to MPI servers for testing. |  | M | Schedule | Medium | ISSUE | Work closely with the MVI/HDR group
|  |  |  | 2015-12-29 | ISSUE: Setting up the systems in the Innovation Sandbox and then the system provided by VIP setup and configuration, then moving to the MVI VistA systems has placed the schedule past the POP. |  | H | Schedule | High | ISSUE | Issue has been communicated to the VA COR. | [5 empty] | Work continues on setting up the systems
|  |  |  | 2016-01-07 | ISSUE: The IOC sites will be unable to set up the system in their test environment based on no connection to an eMI test system. |  | H |  | High | ISSUE | UFT and IOC sites can use the SQA servers to do their initial test.
|  |  |  | 2016-01-22 | ISSUE: Team members need GFE in order to develop the middleware and to do automated testing. |  | H |  | High | ISSUE | The COR is aware of the requirement. It will require a contract modification which the COR is working on.

## Risk ID Log Descriptions
Risk Log Field Descriptions
Project | The formal title or application namespace given to the project.
Program | The formal title or application namespace given to the Program
Project Manager | Name of current Project Manager (may want to include previous PMs in Notes area)
Program Manager | Name of the current Program Manager
Risk Coordinator | Name(s)of the person(s) who identified (or contributed) the risk.
Risk Number | The unique sequential number to identify each risk. ( system-generated unique identifier)
Risk Name (short title) | A short descriptive title of the Risk
Risk Priority | The criteria, or set of conditions, that determine if a risk is no longer a threat and the risk can be closed.
Date Risk Record Opened | System-generated date/time stamp (date field)
Date Risk was Identified | Date/time the Risk was originally identified by the Risk Coordinator (not the Date the Risk was recorded in Risk Log)
Risk Statement/ Description (If…then…) | (in If…Then.. format) The description of the identified risk.
Risk Category | (Project/Program, Operation, OMB) The category to which the risk belongs (e.g., Schedule, Cost, Technical). Categories were defined during Risk Management Planning. (include both Project/Program and OMB 19 Risk Categories/Definitions)
Risk Probability (VH,H,M,L,VL) | The probability or likelihood that the risk will occur (e.g., VL = Very Low; L = Low; P = Probable; H = High; VH = Very High).
Risk Impact (VH,H,M,L,VL) | The impact of the risk to the project, if it occurs (e.g., VL = Very Low; L = Low; M = Moderate; H = High; VH = Very High).
Root Cause | The most basic cause (or causes) that can reasonably be identified that management has control to fix and, when fixed, will prevent (or significantly reduce the likelihood of) the problem’s recurrence.
Risk Response | Risk Response Options (Accept, Avoid, Exploit, Enhance, Transfer, Share, Mitigate) see table below
Risk Response Strategy | Describe reason for selected Risk Response and provide a detailed strategy/action to reduce/eliminate the risk
Risk Trigger | The condition, date, or event that gives an early warning (or trigger) that the event could occur and action must be taken quickly to prevent the risk from becoming an Issue. An event that itself results in the risk event occurring (
Current Status | The current status of the risk (Submitted, Team Reviewed, Analysis Requested, Analyzed, Mitigated, Montinored, Rejected, or Closed)
Follow Up Date | Date/Time Risk is re-visited/Status is updated/Strategy is reassessed
Timeframe (Milestone, Gateway, Increment) | Time frame covers the time from when an incident or crisis happens to the time your business can resume usual operations.
Risk Owner | Name of the person responsible for ensuring the risk response is performed by the Risk Action Officer.
Non-VA Risk/Issue Owner (if applicable) | Name/organization of Risk/Issue Owner external to VA (may want to include Risk/Issue Owners outside OI&T (VBA, VHA,etc.)
Risk Action Officer | The name of the person responsible for the develoment and execution of the the risk mitigation and issue contingency plans.
Risk Escalation History | A set of notes with dates describing the escalation and de-escalation history of the risk
Flags (Red/Yellow) | Actions that require Senior Leadership intervention (Yellow, Red Flags)
TechStats (trigger) | Actions that require Senior Leadership intervention (TechStat) - normally an Issue
Leadership Action Needed (trigger) | Triggered Action for Senior Leadership intervention to assist in the reduction/elimination of the risk. (Action triggered by Red Flag, TechStat, or select Senior Leadership pillar action)
Dependencies | Identify contributing dependencies outside of their control that directly impact the feasability and progress of their own project (specific to the Risk)
Review Board Date (if appropriate) | If Applicable, date when risk was submitted/reviewed by the Program/Pillar Risk Review Board
Retirement Criteria | The criteria, or set of conditions, that determine if a risk is no longer a threat and the risk can be closed.
Issue Contingency Plan (if appropriate) | Contingency Plan (Feasible Courses of Action) if Risk becomes a Critical Issue
Notes | The place to record anything pertaining to the RR that does not already have a column, e.g. communications, changes, decisions, etc.
Product/Platform Management | PPM working with the project/program
Product | 1. The end-deliverable that meets the customer’s need. 2. A product is a collection of capabilities, driven by a business need. Products contain high-level outlines of business needs, architecture plans, KPIs, and cost estimates. Products may align to one or more programs.
Risk Response Options and Example
Risk Response Options | Example
ACCEPT | the project plan is not changed because the opportunity is so small or so unlikely that the risk of change creates a negative risk outweighing the opportunity.
AVOID | the project plan is changed so that it is impossible for the risk to occur because the project is never susceptible to that type of risk. Some risks cannot be avoided.
EXPLOIT | the project plan is changed from the normal approach for this type of project to take advantage of the unusual condition that is occurring.
ENHANCE | the project plan is changed so as to create an opportunity for improvement in the ability of the project to achieve one of its objectives.
SHARE | the project plan is changed so as to bring an outside partner onto the project that creates opportunities to improve one of the project objectives.
TRANSFER | the project plan is changed so that an outside agency assumes responsibility for addressing a portion of the risk impact
MITIGATE | the project plan is changed so that when or if the risk occurs it will only have minor effect because the threat has been anticipated and provisions for addressing it are in place.

## Issue Log
Issue Identification Log (Required Fields *)
Project *: |  |  |  |  | Program*: |  |  |  | Product: |  |  |  |  | Product/Platform Management:
Project Manager*: |  |  |  |  | Program Manager*: |  |  |  | Issue Coordinator*:
Issue ID# * | Issue (short title) * | Issue Priority * | Date Identified/Date Opened * | Issue Description & Original Risk Statement (if applicable)* | Issue Category * | Root Cause * | Project Risk Category/OMB Category | Contingency Action Plan(s) | Impact Ranking (VH, H, M) | FLAGS (Red/Yellow) * | TechStat* | Leadership Actions or Help Needed * | Status * (Open, In Process, Deferred, Resolved, Closed, ReOpen) | Follow-up Date * | Issue Owner* | Risk Owner | Resolution Description | Notes

## Issue Log Description
Issue Log Field Descriptions
Issue Log Field | Description
Project | Name of Project (auto-populated from Risk Log/Registry - if applicable)
Program | Name of Program (auto-populated from Risk Log/Registry - if applicable)
Project Manager | Name of Project Manager(s)
Program Manager | Name of Program Manager
Issue Coordinator | Name of Issue Coordinator (Project, Program, pillar/agency)
Issue ID# | The unique sequential number to identify each Issue. (system-generated)
Issue (short description) | A concise description of the event or condition that has impacted or is currently impacting the project, program, or operational objectives.
Issue Priority | determines which issue is the most urgent and should be solved first, (E.g. the priorities may encompass Immediate, Soon, Later, etc.). Issues will be categorized into levels of importance (Urgent, High, Medium, and Low) based on their impact to the project goals, objectives, scope, schedule, and budget.
Date Identified/Date Opened | The date the Issue was identified. MM/DD/YYYY
Issue Description & Original Risk Statement | Detailed description of the Issue plus the Original Risk(s) statements associated with the Issue. An event or condition that has already happened and has impacted or is currently impacting the project, program, or operational objectives. There is no uncertainty or probability aspect associated with an issue
Issue Category | Issues in the log will be grouped into the following Categories to facilitate review and reporting: Requirements; Design; Development; QA/Testing; Training; Implementation; Architecture/Network Infrastructure; Resources; Project Management; Communications; Dependencies/Interdependencies; External
Project Risk Category/OMB Category | Auto-populated from Risk Log/Registry - if applicable
Root Cause | The most basic cause (or causes) that can reasonably be identified that management has control to fix and, when fixed, will prevent (or significantly reduce the likelihood of) the problem’s recurrence.
Contingency Action Plan | A detailed strategy for handling the Issue, provide a Contingency Plan (Feasible Courses of Action) to address and minimize or eliminate the Issue/Problem
Impact Ranking | how bad the consequence would be if the issue is left unsolved (Minor Moderate Significant Major
Flags (Yellow/Red) | Actions that require Senior Leadership intervention (Yellow, Red Flags)
TechStats | Issues requiring immediate action and Senior Leadership intervention
Leadership Actions or Help Needed | Triggered Action for Senior Leadership intervention (this is a mandatory field for Issues)
Status (Open, In Process, Deferred, Resolved, Closed, ReOpen) | The current status of the Issue: Open – the initial status assigned when a new issue has been identified and added to the log ; In Process – an owner has been assigned and has started working on the issue; Resolved – the owner has identified a solution to the issue and has taken corrective action to resolve; Reopened – an issue was previously categorized Resolved, Deferred, or Closed but has been identified again as a continuing issue; Deferred – the project manager, owner, and issue submitter have decided to postpone addressing the issue to a later time; Closed – the project manager and issue submitter have validated and accepted the the resolution and no longer considers the issue open
Follow-up Date | The date to follow-up on the Issue and assess the current status.
Issue Owner | The name of the person responsible for the develoment and execution of the the issue contingency plans.
Risk Owner | Name of the person responsible for ensuring the risk response is performed by the Risk Action Owner. Usually the Program manager or their designee.
Resolution Description | Description on the details and actions taken to resolve the Issue and Lessons Learned
Product/Platform Management | PPM working with the project/program
Product | 1. The end-deliverable that meets the customer’s need. 2. A product is a collection of capabilities, driven by a business need. Products contain high-level outlines of business needs, architecture plans, KPIs, and cost estimates. Products may align to one or more programs.
Notes | The place to record anything pertaining to the issue record that does not already have a column, e.g. communications, changes, decisions, etc.
Issue Impact Factors
Issue Impact Factors | Description
Reputation | Issues impacting key constituents' perceptions of the VA's values, commitments, behaviors, and integrity
Finance | Issues directly impacting the project, program, organizations budget
Regulatory | Issues impacting VA agencies license to operate, access to customers/stakeholders, and the nature and time of legislative or regulatory actions, fines and penalties
Legal | Issues impacting current (or the potential for future) litigation.
Issue type – Define the categories of issues that you're likely to encounter. This helps you track issues and assign the right people to resolve them. You could have broad descriptions like these:
Technical – Relating to a technological problem in the project.
Business process – Relating to the project's design.
Change management – Relating to business, customer, or environmental changes.
Resource – Relating to equipment, material, or people problems.
Third party – Relating to issues with vendors, suppliers, or another outside party.
Status – Track the progress of the resolution with a clear label identifying the issue's overall status. Here's an example:
Open – The issue has been identified, but no action has yet been taken.
Investigating – The issue, and possible solutions, are being investigated.
Implementing – The issue resolution is in process.
Escalated – The issue has been raised to management or the project sponsor/steering committee, and directions or approval of a solution is pending.
Resolved – The resolution has been implemented, and the issue is closed.

## OMB Risk Categories
OMB Risk Categories
Category | Definition | Examples | Mitigation Example
01. Schedule | Risks associated with completion dates (start and finish dates), milestone dates, deliverable dates and the critical path including time allocated for performing work activities, activity dependencies and durations. | (1) Planning has the potential to become more complex than anticipated and could require significantly more time than estimated. (2) Implementation is dependent upon the completion of other projects/activities; their delay would also cause this project to be delayed. | When there is a dependency on another system, identify methods to regularly monitor any schedule changes for that project that may impact this project.
02. Initial Cost | Risks associated with the quality of cost estimates and the ability to secure and manage budgetary resources for what is needed during the planning, preliminary engineering, and project design phase. | (1) Estimates are based on interdependent projects that cannot be analyzed as a single entity and project design and engineering is one of those interdependencies. (2) The project will use new and relatively unproven technologies where there is no comparable VA or Federal example to benchmark preliminary design or engineering costs. | When future contracting costs are going to be based on assumptions rather than benchmarked on an existing VA system, plan to issue a Request For Information (RFI) that requests firms who have expertise in that area to submit their best estimates for initial costs.
03. Life-Cycle Costs | Risks associated with insufficient funds to take the project through the overall process of developing an IT system from investigation of initial requirements through analysis, design, implementation, maintenance and disposal. | (1) Estimates are based on many life-cycle cost assumptions (e.g., inflation rates). (2) Life cycle costs can exceed estimates if the reliability of a system falls below projections. (3) Errors may exist in the cost estimating technique used to derive the life-cycle costs. | To minimize the possibility of miscalculations, use VA approved/accepted methodology for developing estimates and be able to justify it.
04. Technical Obsolescence | Risks associated with technology supporting the investment will become obsolete by follow-on technology. This could be due to key technologies losing value because a new, more functional product or technology supersedes it or when the deliverable(s) become less useful or useless due to changes in other products before the project has completed its full functional life-cycle. | (1) Strategies for avoiding the use of outdated technical resources over the system life-cycle have not been incorporated into the project plan. (2) There is no plan for regular technology upgrades or refreshes. | Discuss with the software/hardware provider regarding its plans to upgrade versions/products and conduct independent research on the possibility; incorporate these plans into the project’s cost and schedule.
05. Feasibility | Risks associated with a process, design, procedure, or plan can be successfully accomplished in the required time frame as proposed. These risks impact the overall likelihood of the success of the investment. | (1) The affected office(s) may not have the existing capability to successfully develop or implement the project within defined technical, scope, and schedule parameters. (2) There are no examples of successful implementation of the proposed approach, software, or hardware within public or private industry. | Find reviews of organizations that have successfully implemented the product/technology to be used. If none exist for the version being used, research any existing reviews on earlier versions.
06. Reliability of Systems | Risks associated with a system not performing its intended function(s) for a specified period of time when operating under normal conditions. | (1) The project may not have the ability to provide information about current or planned / desired system reliability. (2) The proposed system is new and there may be no commercial or government installations to benchmark for actual reliability data. | Use a beta-test to establish reliability standards.
07. Dependencies and Interoperability Between Systems and Others | Risks associated with the project will fail because it depends upon the successful completion of another system, or the project will not be able to function/operate with other systems or products without an unplanned special effort. | (1) Reliance on interoperability with other systems (existing or in development) within the Department and/or across the Federal Government (e.g. technical interfaces, schedule dependencies). (2) The project is directly linked to the long-term success, implementation or on-going maintenance of other systems. | Set up regularly scheduled meetings with the managers of the other systems critical to this project to discuss plans for modifications, updates, and compatibility issues.
08. Surety (Asset Protection) Considerations | Risks associated with the ability of the project to meet its obligations or when there is some public or private interest which requires protection from the consequences of a contractor’s default or a project's delinquency. | (1) The loss or damage that may result from a contractor failing to deliver as promised. (2) The potential for substantial loss of capability of the project due to an unforeseen disaster and a lack of continuity of operations and/or disaster recovery plans. | Work with security to develop/update continuity of operations / disaster recovery plan for your system. Have program code put into a source code escrow or repository in case of default, bankruptcy, or other unforeseen event by the vendor.
09. Risk of Creating a Monopoly for Future Procurements | Risks associated with the use of closed or proprietary software/source code, as well as dependence on a single vendor or product which in turn creates a risk that in the future the contractor will be able to reap windfall profits by charging excessive costs or reducing service quality. | (1) The inability to conduct open competition in the future due to a current or planned procurement. (2) Use of non-Open Source code software. (3) The inability to connect with existing or planned Department systems without extensive customization | Work with Enterprise Architecture to ensure software solution’s compatibility with future plans for the computing environment of the Department.
10. Capability of Agency to Manage the Investment | Risk associated with the ability, experience, and capability of personnel to manage at the project and investment level. These risks may include PM experience in managing projects of similar scope and size; availability of appropriate management tools, availability of managerial and technical training; and the degree of commitment from senior management. | (1) Project Manager(s) does not have a PMP or equivalent certification. (2) Earned value data show unexplained project cost and/or schedule variances of over 10 percent. (3) Contractors do not use Earned Value reporting. | Ensure that all contractors will use a compliant Earned Value Management System that provides Department specified data.
11. Overall Risk of Project Failure | Risks associated with project failure due to inherent project weaknesses such as the project missing a clear link between it and the organization’s key strategic priorities, including agreed measures of success. | (1) Veterans and health providers that are the customers for the project’s deliverables may desire a different solution. (2) Investment solution may be overtaken by activities being pursued outside the Department (e.g., centralization of government functions into Centers of Excellence). | Demonstrate continuous customer involvement in setting and monitoring project measures of success.
12. Organizational and Change Management | Risks associated with organization/agency/government-wide cultural resistance to change. These include bypassing, lack of or improper use or adherence to new systems and processes due to organizational structure and culture; or inadequate training plan. | (1) Organizational and/or Department cultural resistance to proposed process change may be high. (2) Extensive employee training may be required in order to apply benefits of investment to existing or proposed process. (3) Initial operation of the new system demonstrates lack of use, improper use, or failure to fully use due to unchanged organizational structure or process. | Schedule and hold regularly scheduled meetings with appropriate customers and stakeholders to become aware of their concerns; coordinate the timing of their training, etc. to match the relevant milestones and outputs of the investment.
13. Business | Risks associated with the potential that an investment will fail to achieve the expectations of the project’s owners and customers. These risks involve potential failure of alternatives resulting in process efficiencies and streamlining, or risks that the overall targeted effectiveness will not be achieved. | (1) Investment’s statements of support of Department customers not carried through in project outcomes. (2) Investment planning has little or no customer involvement. | Demonstrate continuous customer involvement.
14. Data/Information | Risks associated with data/information loss or disruptions caused by natural disasters (hurricanes, tornadoes, floods, earthquakes, etc.) or by area-wide disruptions of communication or electric power or malicious attacks. In addition, it can also include the ability of the investment to obtain, store, produce, share, and manipulate data as planned. | (1) No contingency plans exist to deal with the loss/misuse of data or information. (2) Project may not be able access data from other sources (federal, state and/or local agencies). | Develop and test a contingency plan for data protection, for systems in development testing could be accomplished using table top exercises.
15. Technology | Risks associated with immaturity of commercially available technology, new technologies, or risks of technical problems/failures with applications and their ability to provide planned and desired technical functionality. These risks also extend to the problems related to the use of technologies new to the Department, new software releases, or hardware new to the market. | (1) Immaturity of commercially available technology. (2) Technical problems/failures associated with applications to be used. (3) Inability to provide planned and desired technical functionality. (4) Possibility that the application of software engineering theories, principles, and techniques will fail to yield the appropriate software product. (5) Final product will be overly expensive, delivered late or otherwise unacceptable to the customer. | Maintain open lines of communication with software/hardware manufacturer(s) to stay abreast of any new installations that may occur at a Federal Department, or elsewhere, and incorporate those lessons learned into the project plan.
16. Strategic | Risks associated with strategic/Government-wide goals. The risk of misalignment with Department Mission and Strategic Goals, and/or the Presidents Management Agenda. | (1) The investment fails to achieve those strategic goals it states it will support. (2) Project objectives are not clearly linked to the Department’s overall strategies or to Government-wide policies and standards. | Plan to do periodic reviews of the investment’s objectives to ensure its alignment with Department’s Strategic Plan and/or Enterprise Architecture.
17. Security | Risks associated with the security/vulnerability of systems, Web sites, information and networks; risks of intrusions and connectivity to other (vulnerable) interconnected systems. These risks encompass misuse of information (criminal/fraudulent) leading to not meeting Department and/or federal security standards. | (1) The investment does not have a current, accurate, and implemented security plan. (2) The systems associated with the investment do not have an Authorization to Operate (ATO) or are not compliant with the Assessment and Authorization process outlined in NIST Special Publication 800-37 Rev 1. (3) The project’s contractors are not in full compliance with Department or federal security requirements. (4) Security training is not at 100 percent compliance. [Note: For this risk category, in the risk description you must mention the level of risk (high, moderate, or basic/low) and the aspect of security determines the level of risk.] | Plan to fully conform to all Department security requirements within; provide projected and specific dates for each component. Initiate an effort to achieve a 100 percent participation in security training within 3 months.
18. Privacy | Risks associated with possible violation of the legal restrictions on the collection, use, maintenance, and release of information about individuals. | (1) Investment may feature a publicly accessible web site with personal data links. (2) Investment may involve a process that collects, manipulates, stores, or shares personally identifiable information. (3) Investment may convert paper files with personal data to electronic files. | Designate staff to ensure that privacy concerns and requirements are addressed in every phase of the investment. Coordinate with the Department’s Privacy Advocate or Privacy Office.
19. Project Resources | The risk associated with factors impacting the performance and delivery of project resources such as personnel, subcontractors, tools, software, hardware, equipment and facilities. Risks pertain to assets available or anticipated; including people, equipment, facilities and other things used to plan, implement, and maintain your project. | (1) The scope of the investment is not clear. (2) Necessary project resources are not clearly or completely specified. (3) No examples of a successful approach to solving the problem are provided in either project description or in discussion of alternatives. | Establish a task force of project staff and customers who will monitor the investment to ensure continued relevance to the problem being addressed and that appropriate resources are requested.

## Yellow Flag Risk Categories
Yellow Flag Category | Description
1. Critical Personnel Resources Turnover | Any changes to personnel resources which are critical to successful project execution such as Business Sponsor, Project Manager, Solution Architect, Business Analyst, Contractor PM.
2. IPT Membership Change and/or Performance Issues | Any changes to the business SMEs; Lack of sufficient participation by IPT members; Lack of representation by any key stakeholder organization in the IPT.
3. Requirements Changes | Any significant change to the business and/or technical requirements that can impact the successful project execution.
4. Change in Acquisition / Contract Strategy | Changes to the contract type; modification to the existing contract.
5. Change in the Funding Status | If project adjusted or lost future/current year’s funding.
6. Change in Architecture & Technical Environment | Any need to change the solution architecture, technology platform used, or the technology vendor; any new technical dependency; Significant risks in the setup of technical (development, testing, or pre-production) environments, as well as changes to the hosting location, and CRISP impact.
7. System or Data Dependencies | Delays or issues due to interfaces between projects (upstream and downstream)
8. Significant Change in Development Team Composition and/or Competency | Any significant change in the composition and/or competency of the development team (government or vendor)
9. Missed Inter-Increment Key Milestone (UPMs) | Any missed inter-increment milestone date that does not threaten the increment ‘s completion date
10. Data Reporting Inaccuracies | Projects which appear on the PMAS Anomaly Report for 2 consecutive weeks or more will receive this flag from the PMAS Business Office
11. Budget Tracking Tool (BTT) Obligation Date Risk | For projects that do not have a date populated as the Acquisition Package Start date in BTT, a yellow flag will be generated by the PBO as this is an indication that the acquisition package has not yet been started. Subsequent flags may be generated if Projected package Submittal date, Projected Actionable package date and Projected Award date are missing.
12. Other | For projects that need to raise a risk, which is not described by the other YF categories. Submitter must provide a 1-3 sentence issue description, which explains the reason and risk for the YF.