## Slide 1: One VA Pharmacy VA118-15-F-0663
Kickoff Meeting Agenda
Deliverable 0001AB
Business Information Technology Solutions, Inc. (BITS)
3190 Fairview Park Drive, Suite 350
Falls Church, VA 22042

## Slide 2: Agenda
Introductions
COR Administrative Items
OneVA Pharmacy Scope
Program Goals and Objectives
Summary of Tasks: High Level Plan
Contract Deliverables Schedule Overview. Critical Success Factors and Project Acceptance Criteria
The BITS Team Organization
Housekeeping Matters
Next Steps / Discussion Items
Open Discussion

## Slide 3: Introductions The BITS Team
Prime Contractor
Business Information Technology Solutions (BITS) is a Service Disabled Veteran Owned Small Business (SDVOSB) specializing in project management, configuration management, system engineering, system enhancements, system development and technical enterprise solutions. BITS provides services to government and commercial clients in the health, human resource, and financial domains.
Subcontractor
An innovative data-centric solutions provider delivering unique concepts, capabilities, and tools in various areas. A long, successful history supporting Federal agencies on projects involving legacy healthcare system integration, data warehousing, digital healthcare data, and electronic health records, and service oriented architecture (SOA).
SRA data scientists’ solutions facilitate access, control, and delivery of standards based actionable data for VA and MHS healthcare systems including integration with other federal, civilian, and commercial healthcare systems.
(Former Qbase)

## Slide 4: OneVA Pharmacy Scope
The BITS Team will develop a software product, which will modify the existing VistA software allowing OneVA pharmacies to make changes and address prescriptions through a middleware model that meets the current VA standards. This work will include the removal of controlled substances from the active refill list.
Our Team will develop and provide all documentation, complete all testing activities, and facilitate training for the product consistent with IOC delivery of the capability. BITS will provide a tailored set of PMAS documents consistent with the identified approach.

## Slide 5: Program Goals and Objectives
Portability of Prescriptions
  Benefits to Veterans
    More immediate service
    Improved medication reconciliation
  Improved Employee Engagement
  Improved Access and Portability

## Slide 6: Summary of Tasks: High Level Plan
Program management, Reporting Requirements, and Code in Flight
(task 1)
Primavera Project Schedule/Updates
Software Development
(Task 3)
Testing
(Task 4)
Software Development Planning
(Task 2)
Signed Requirements Specification Document (RSD)
Business Requirements Document (BRD)
Project Management Plan(PMP)
VAs Rational Requirements Composer (RRC)
Software Requirements
RTC Entry of all development related RTC tasks
Operational Acceptance Plan
Approved Source Code
Planning
Unit , SQA, and User Functional Testing
Operational Readiness
Initial Operating Capability (IOC) Testing
Monthly Progress Report and Progress Meeting Minutes
Kick-off Meeting
Risk Issue Log/Updates
Code in Flight
Project Coordination and Integration
Create Epics, User Stories and Tasks in Rational Tools Composer (RTC)
System Design Document (SDD)
Production Operations Manual
Updated Approved ProPath Required Documentation
Required and Approved ProPath IOC Documentation
Introduction to VistA Intake Program

## Slide 7: Contract Deliverables Schedule Overview, Critical Success Factors and Project Acceptance Criteria
CLIN | Description | Due Date
0001 | Project Management Plan (includes all deliverables and labor associated with PWS paragraph 5.1) | Monthly
0001AA | Project Management | 30 DAC and monthly
0001AB | Kick-off Meeting Agenda / Kick off Meeting | 5 Business DAC/12 DAC
0001AC | Primavera Project Schedule | 10 DAC
0001AD | Risk Issue Log | 30 DAC
0001AE | Monthly Progress Report | 5th of each month
0001AF | Progress Meeting Minutes | 2 days after 0001AE
0001AG | Updated Primavera Project Schedule | 30 days after updates
0001AH | Updated Risk Issue Log | 5 days after updates

## Slide 8: Contract Deliverables Schedule Overview, Critical Success Factors and Project Acceptance Criteria
CLIN | Description | Due Date
0001AJ | Open Source Code in Flight Submission | 30 DAC
0001AK | IPT Meeting Minutes | 3 days after IPT meeting
0001AL | Daily Stand Up Call Meeting Minutes | 2 days after meeting
0002 | OneVA Pharmacy Software Development Planning (includes all labor and deliverables associated with PWS paragraph 5.2) | 
0002AA | Requirements Specification Documentation | 30 DAC/monthly
0002AB | RRC and RTC Entry (PWS paragraph 5.2) | 30 DAC/monthly
0002AC | System Design Document | 30 DAC/monthly

## Slide 9: Contract Deliverables Schedule Overview, Critical Success Factors and Project Acceptance Criteria
CLIN | Description | Due Date
0003 | Software Development IAW (PWS paragraph 5.3) | 
0003AA | Approved Source Code | 90 DAC/monthly
0003AB | Updated and Approved Propath Required Documentation | 90 DAC/monthly
0003AC | Required and Approved ProPath IOC Documentation | 90 DAC/monthly
0004 | Testing IAW (PWS paragraph 5.4) | 
0004AA | Signed Master Test Plan | 90 DAC/monthly
0004AB | Peer and User Reviewed and Approved Test Cases and Test Scripts | 90 DAC/monthly
0004AC | Testing Related Tasks | 90 DAC/monthly

## Slide 10: Contract Deliverables Schedule Overview, Critical Success Factors and Project Acceptance Criteria
CLIN | Description | Due Date
0004AD | Signed IOC Site Memorandum of Understanding | 90 DAC/monthly
0004AE | Risk Analysis and Testing Scope Report (RATSR) into Master Test Plan | 90 DAC/monthly
0004AF | Primary Developer Checklists | 120 DAC/monthly
0004AG | Secondary Developer Checklists | 120 DAC/monthly
0004AH | Updated and Approved Test Cases and Test Scripts with Results | 120 DAC/monthly
0004AJ | HP Fortify Static Code Analyzer Scan Results | 120 DAC/monthly
0004AK | Product Build for SQA Testing | 120 DAC/monthly

## Slide 11: Contract Deliverables Schedule Overview, Critical Success Factors and Project Acceptance Criteria
CLIN | Description | Due Date
0004AK | Updated Test Cases and Test Scripts and Results | 120 DAC/monthly
0004AM | Updated Requirements Traceability Matrix | 120 DAC/monthly
0004AN | Product Built Test Evaluations | 120 DAC/monthly
0004AP | Product Build VistA SQA Checklists | 120 DAC/monthly
0004AQ | UFT Test Cases and Test Scripts with Results | 120 DAC/monthly
0004AR | Signed Customer Acceptance Form | 120 DAC/monthly
0004AS | IOC Entry Request and Exit Summary | 120 DAC/monthly

## Slide 12: Contract Deliverables Schedule Overview, Critical Success Factors and Project Acceptance Criteria
CLIN | Description | Due Date
0004AT | IOC Site Evaluation Defect Log and Concurrence Statement | 120 DAC/monthly
0005 | Introduction to VistA Intake Program | 
0005AA | Lesson Learned Reports | 60 DAC/monthly
0005AB | Implementation Report | 60 DAC/monthly
0010 | Contractor Staff Roster | 3 DAC/updates
0011 | Final Section 508 Compliance | 5 Days after testing is completed

## Slide 13: The BITS Team Organization

## Slide 14: Housekeeping Matters
Risks and Issues Management and Escalation Processes
Communication Strategy (Internal and External)
  Escalation of problems to Project Manager
  Confidential information
Change Management, working with the COR
Ground Rules and Logistics
  Team meeting schedules
  Accurate daily time reporting
  Requests for time off

## Slide 15: Next Steps / Discussion Items
On-Boarding with Zelia Taylor-Pearson
Access to original development sites within Innovation Sandbox
Use of Subject Matter Experts (SME)

## Slide 16: Open Discussion